## Blad1
Route | Method | Klar | Ansvar | Route path ok | Route commented (one line enough) | Promise handling | Tested | Handles roles | Input validation | Returns JSON | Documented | Additional comments
/api/courses/ | GET | n | Bosse | Y | y | Y | n | y | y | Y | Y | PÅVERKAS AV NYA MEMBER SYSTEMET
/api/courses/ | POST | n | Bosse | Y | y | Y | check | y | y | Y | Y | PÅVERKAS AV NYA MEMBER SYSTEMET
/api/courses/:course_id | GET | n | Bosse | Y | Update comment | N | Check | N | N | Y | Y | PÅVERKAS AV NYA MEMBER SYSTEMET
/api/courses/:course_id/students | GET | n | Bosse | NEW: api/courses/:course_id/members | y | y | No | y | y | y | Y | PÅVERKAS AV NYA MEMBER SYSTEMET
/api/courses/:course_id/students/invite | GET | n | Bosse | NEW: api/courses/:course_id/members/invite | Y | Y | N | Y | Y | Y | Y | merga pending coh invite
/api/courses/:course_id/students/invite | POST | n | Bosse | NEW: api/courses/:course_id/members/invite | Y | Y | n | Y | Y | y | Y | PÅVERKAS AV NYA MEMBER SYSTEMET
/api/courses/:course_id/students/invite | PUT | n | Bosse | NEW: api/courses/:course_id/members/invite | y | Y | n | Y | Y | y | Y | merga pending coh invite
/api/courses/:course_id/students/invite | DELETE | n | Bosse | NEW: api/courses/:course_id/members/invite | y | Y | n | Y | Y | y | Y | merga pending coh invite
/api/courses/:course_id/teachers | GET | n | Bosse | MERGED: api/courses/:course_id/members
/api/users/me/courses | GET | n | Bosse | NEW: api/users/me/member | y | Y | Check | Y | Y | Y | Y | PÅVERKAS AV NYA MEMBER SYSTEMET
/api/users/me/teaching | GET | n | Bosse | MERGED: api/users/me/member
/api/users/courses/invite | GET | n | Bosse | NEW: api/users/me/invites | y | y | n | y | y | y | Y
/api/users/courses/:course_id/status | GET | n | Bosse | NEW: api/users/me/:course_id/status | y | y | n | y | y | y | Y | PÅVERKAS AV NYA MEMBER SYSTEMET
/api/courses/:course_id/students | DELETE | n | Bosse | NEW: api/courses/:course_id/members | Y | N | N | Y | Y | N | Y | PÅVERKAS AV NYA MEMBER SYSTEMET
/api/courses/:course_id/teachers | PUT | n | Bosse | NEW: api/courses/:course_id/members | Y | Y | N | Y | Y | N | Y | PÅVERKAS AV NYA MEMBER SYSTEMET
/api/users/:user_id | GET | n | Bosse | y | n | Y | y | N | n | y | Y | PÅVERKAS AV NYA MEMBER SYSTEMET
/api/courses/me | GET | n | DONT REMOVE YET
/api/courses/:course_id/students | PUT | n | DONT REMOVE YET
/api/courses/:course_id/students/pending | GET | n | DONT REMOVE YET
/api/courses/:course_id/students/pending | POST | n | DONT REMOVE YET
/api/courses/:course_id/students/pending | PUT | n | DONT REMOVE YET
/api/courses/:course_id/students/pending | DELETE | n | DONT REMOVE YET
/api/courses/:course_id/teachers | DELETE | n | DONT REMOVE YET
/api/users/:user_id/submissions | GET | n | DONT REMOVE YET
/api/users/:user_id/courses | GET | n | DONT REMOVE YET
/api/users/:user_id/courses | POST | n | DONT REMOVE YET
/api/users/courses/pending | GET | n | DONT REMOVE YET
/api/users/:user_id/courses/:course_id/submissions | GET | n | DONT REMOVE YET
/api/users/ | GET | n | DONT REMOVE YET
/api/users/me | PUT | n | DONT REMOVE YET
/api/courses/:course_id/assignmentgroups | POST | y | Henrik | bar: y to Y
/api/courses/:course_id/assignmentgroups | GET | y | Henrik | bar: y to Y
/api/courses/:course_id/assignmentgroups/:assignmentgroup_id | GET | y | Henrik | bar: y to Y
/api/courses/:course_id/assignmentgroups/:assignmentgroup_id | PUT | y | Henrik | bar: y to Y
/api/courses/:course_id/assignmentgroups/:assignmentgroup_id | DELETE | y | Henrik | bar: y to Y
/api/courses/:course_id/enabled_features | GET | Y | Henrik | bar: y to Y
/api/courses/:course_id/badges | GET | Y | Henrik | bar: y to Y
/api/courses/:course_id/badges | POST | Y | Henrik | [8 empty] | Change route, /api/courses/:course_id/badges | bar: y to Y
/api/courses/:course_id/badges/:badge_id | GET | Y | Henrik | [8 empty] | Change route, /api/courses/:course_id/badges/:badge_id | bar: y to Y
/api/courses/:course_id/badges/:badge_id | PUT | Y | Henrik | [8 empty] | Change route, /api/courses/:course_id/badges/:badge_id | bar: y to Y
/api/courses/:course_id/badges/:badge_id | DELETE | Y | Henrik | [8 empty] | Change route, /api/courses/:course_id/badges/:badge_id | bar: y to Y
/api/courses/:course_id/features | GET | Y | Henrik | [8 empty] | Change route, /api/courses/:course_id/features | bar: y to Y
/api/courses/:course_id/features/me | GET | Y | Henrik | [8 empty] | Change route, /api/courses/:course_id/features/me | bar: y to Y
/api/search/ | GET | Y | Henrik | bar: y to Y
/api/tester/languages | GET | Y | Henrik | bar: y to Y
/api/courses/:course_id/assignments | GET | m | Mikael | y | Y | Y | Y | get hidden? | Y | Y | changed
/api/courses/:course_id/assignments/:assignment_id | GET | m | Mikael | y | Y | Y | Y | get hidden? | Y | Y | changed | Kolla så att assignemnt är i kursen (done)
/api/courses/:course_id/assignments | POST | Y | Mikael | bar: y to Y
/api/courses/:course_id/assignments/:assignment_id | PUT | Y | Mikael | [8 empty] | Kolla så att assignemnt är i kursen (done) | bar: y to Y
/api/courses/:course_id/assignments/:assignment_id/tests | GET | Y | Mikael | [8 empty] | Kolla så att assignemnt är i kursen (done) | bar: y to Y
/api/courses/:course_id/assignments/:assignment_id/tests | POST | Y | Mikael | [8 empty] | Kolla så att assignemnt är i kursen (done) | bar: y to Y
/api/courses/:course_id/assignments/:assignment_id/tests/:test_id | PUT | Y | Mikael | [8 empty] | Kolla så att assignemnt är i kursen (done) | bar: y to Y
/api/courses/:course_id/assignments/:assignment_id/tests/:test_id | DELETE | Y | Mikael | [8 empty] | Kolla så att assignemnt är i kursen (done) | bar: y to Y
/api/courses/:course_id/assignments/:assignment_id/tests/:test_id | GET | Y | Mikael | [8 empty] | Kolla så att assignemnt är i kursen (done) | bar: y to Y
/api/courses/:course_id/assignments/:assignment_id | DELETE | Y | Nils | bar: y to Y
/api/courses/:course_id | DELETE | Y | Nils | bar: y to Y
/api/courses/:course_id | PUT | Y | Nils | bar: y to Y
/api/users/me | GET | Y | Nils | [8 empty] | Inte ge ut Token-field | bar: y to Y
/api/courses/:course_id/assignments/:assignment_id/submit | POST | Y | Tobä | [8 empty] | Använd asserten för att kolla passed == true, kolla så att assignmenten har tester? | bar: y to Y
/api/courses/:course_id/assignments/:assignment_id/draft | POST | y | Tobä | [8 empty] | checkIfAssignmentInCourse kommer påverkas av nya course schemat | bar: y to Y
/api/courses/:course_id/assignments/:assignment_id/draft | GET | y | Tobä | [8 empty] | checkIfAssignmentInCourse kommer påverkas av nya course schemat | bar: y to Y
l33t route

## Blad2
2017-12-05 14:55:50
Route | Klar |  | Ansvarig | Hur backends route ser ut(om ändrad) | Övriga noteringar
return this.apiPut('/api/courses/' + id, body); | Y |  | Nils
return this.apiPost('/api/courses', body); | Y |  | Bosse
return this.apiGet('/api/users/me/teaching'); | Y |  | Bosse | /api/users/me/member | både teaching och student
return this.apiGet('/api/users/me/courses'); | Y |  | Bosse | /api/users/me/member | både teaching och student
return this.apiGet('/api/users/me'); | Y |  | Nils
return this.apiGet('/api/users/courses/' + course_id + '/status'); | Y | Används ej | Bosse | /api/users/me/:course_id/status
return this.apiGet('/api/users/' + user_id + '/courses'); | Gone | Används ej | Bosse | Borttagen. Behövs denna?
return this.apiGet('/api/users/' + id.get()); | N | Används ej | Bosse | Använd?
return this.apiGet('/api/courses/' + id); | Y |  | Bosse |  | Student&teacher fält bytt mot member fält
return this.apiGet('/api/courses/' + course_id + '/features/me'); | Y |  | Henrik
return this.apiGet('/api/courses'); | Y |  | Bosse
return this.apiDelete('/api/courses/' + course_id, body); | Y |  | Nils
return this.apiPost('/api/courses/' + course_id + '/assignmentgroups', body); | Y |  | Henrik
return this.apiGet('/api/courses/' + id + '/students'); | Y |  | Bosse | /api/courses/:course_id/members | teachers och students
return this.apiPut('/api/courses/' + course_id.get() + '/students', body); | N | Används ej | Bosse | /api/courses/:course_id/members
return this.apiGet('/api/courses/' + course_id + '/features'); | Y |  | Henrik
return this.apiPost('/api/courses/' + course_id + '/badges', body); | Y |  | Henrik
return this.apiGet('/api/courses/' + course_id + '/enabled_features'); | Y |  | henrik
return this.apiGet('/api/courses/' + course_id + '/assignments'); | Y |  | Henrik
return this.apiGet('/api/courses/' + course_id + '/assignments/' + assignment_id); | Y |  | Henrik
return this.apiPost('/api/courses/' + course_id + '/assignments/', body); | Y |  | Henrik
return this.apiPost('/api/courses/' + course_id.get() + '/assignments/' + assignment_id.get() + '/submit', body); | Y |  | Tobbe
return this.apiPost('/api/courses/' + course_id.get() + '/assignments/' + assignment_id.get() + '/save', body); | Y |  | Tobbe | /api/courses/:course_id/assignments/:assignment_id/draft
return this.apiGet('/api/courses/' + course_id.get() + '/assignments/' + assignment_id.get() + '/draft'); | Y |  | Tobbe
return this.apiGet('/api/courses/' + course_id.get() + '/assignments/' + assignment_id.get() + '/tests'); | y |  | Mikael
return this.apiPost('/api/courses/' + course_id + '/assignments/' + assignment_id + '/tests', body); | y |  | Mikael
return this.apiGet('/api/users/courses/invite'); | Y |  | Bosse | api/users/me/invites | Both invites and pending
return this.apiPost('/api/courses/' + course_id + '/students/invite', body); | Y |  | Bosse | api/courses/:couse_id/members/invite | Make sure to pass body variable
return this.apiPut('/api/courses/' + course_id + '/students/invite', {'student_id': student_id}); | Y |  | Bosse | api/courses/:couse_id/members/invite | Make sure to pass body variable
return this.apiDelete('/api/courses/' + course_id + '/students/invite', body); | Y |  | Bosse | api/courses/:couse_id/members/invite | Make sure to pass body variable
return this.apiGet('/api/users/courses/pending'); | Y |  | Bosse | api/users/me/invites | Both invites and pending
return this.apiGet('/api/courses/' + course_id + '/students/pending'); | Y |  | Bosse | api/courses/:couse_id/members/invite | Merged with api/courses/:course_id/members/invite. Query Param type = invite ¦¦ pending
return this.apiPut('/api/courses/' + course_id + '/students/pending', body); | Gone |  | Bosse | api/courses/:couse_id/members/invite | Merged with api/courses/:course_id/members/invite
return this.apiPost('/api/courses/' + course_id + '/students/pending', body); | Gone |  | Bosse | api/courses/:couse_id/members/invite | Merged with api/courses/:course_id/members/invite
return this.apiDelete('/api/courses/' + course_id + '/students/pending', body); | Gone |  | Bosse | api/courses/:couse_id/members/invite | Merged with api/courses/:course_id/members/invite
return this.apiGet('/api/search?query=' + query); | Y |  | Henrik
return this.apiGet('/auth/login/ltu?ticket=' + ticket + '&service=' + service);